## Comment resolution sheet
Comment resolution sheet - review comments approved by the engineer
Run c9e39d901d9e · round 2 · exported 2026-10-20T13:32:35+00:00 · DEMO BY PITCHAI - SYNTHETIC DATA
No. | Document number | Revision | Location | Requirement(s) | Source reference | Comment | Type | Priority | Method | Confidence | Reviewer | Decision date | Vendor response | Close-out
1 | NCT-PRC-PID-0302 | C1 | layer VALVES · block VALVE_BALL #CA - "CL600" | NCT-R-VLV-005 | NCT-MEC-SP-0007 Rev B §4.5 | 'CL600' is not an allowed value; NCT-MEC-SP-0007 Rev B §4.5 allows only: Class 900. | non-compliance | High | rule | 0.93 | Engineer (demo) | 2026-10-20
2 | NCT-PRC-PID-0302 | C1 | layer INSTR · block INSTR_BUBBLE #DB - "120-TT-2012" | NCT-R-INS-010 | NCT-INS-SP-0002 Rev 1 §4.2 | 120-TT-2012 appears on this document but not in the instrument index NCT-INS-IL-0501 (NCT-INS-SP-0002 Rev 1 §4.2). | inconsistency | Medium | rule | 0.95 | Engineer (demo) | 2026-10-20
3 | NCT-QAC-ITP-0901 | A | p. 1 · § 3 Inspection and test activities · table row 5 '4' - "Extent of examination: 10% of girth welds; acceptance per specification" | NCT-R-PIP-010 | NCT-PIP-SP-0003 Rev B §5.1 | Extent of examination is 10 %, below the minimum of 100 % required by NCT-PIP-SP-0003 Rev B §5.1. | non-compliance | High | rule | 0.96 | Engineer (demo) | 2026-10-20